## Sheet1
S/N | Immediate Actions Taken | Short Event Description | Classification
| 220 transformer with out lew sticker use it, inform to them check and lew sticker put by LEW | 52FA11 | electrical
108 | Hand rail missing and put back for access and egress | South plot | Access and egress
842 | Using Excavator to hacking works the operator no wearing ear muff | South culvert 1 | PPE
| Brief workers to drink more water in hot weather conditions to prevent dehydration | TU4 area | Health
195 | Advised crane operator to keep recording in the logbook regularly. | Failed to update the mobile crane logbook by operator. South plot-62AD05, Basin. | Lifting
428 | Upper Concourse Level unused scissor lift no barricade, i inform to subcon supervisor to put barricade the scissor lift if they did not use. | Upper Concourse Level | Fatal zone
| Do not have proper handrail with access ladder | Entrance C | access and egress
939 | Briefed teams to comply strictly | Hacking works carried out without proper ear protection,hand gloves and face shield. Could causes of eye injury and hearing loss-South plot , U 52 -MH -C-01 | PPE
187 | Rebar area inform to them provide metal blank for walk way | Basin at south, 62AD05 | Access and egress
| Boom lift was parked at slope area did not provide wheel shock | Gate 5 | supervision
520 | Installation of metal beam, worker didn’t wear hand gloves can be get finger injury, have advised to wear hand gloves | Entrance E | PPE
| Excavation area no fatal zone barriers are covered, which may cause a person to slip or fall and some times severe injuries may happen. So, immediately ask the worker to put the barriers around. | West plot : N-51 excavation area | fatal zone
| Work area keep clean and tidy up always | W -63-AD-05 | housekeeping
| Inform the sub con supervisor to bend the protuding rebar or put the cap | Helmet identification sticker. | protruding object
244 | Silt fence repair | West Plot last IC | Environmental
534 | Stop the activity ask to do Housekeeping immediately | West plot , J56 Pedestal area poor housekeeping | Housekeeping
31 |  | Loose materials scattered on working platform,.potential falling object hazard | Falling object
954 | Instructed Chuan Lin to install standard rabar protection. However, Chuan Lin claimed that this is not under their scope of work. Reabr protection shall be done by GPL instead | Admin Building - improper rebar protection on all rc cut off piles | Protruding Object
862 | Briefing and advice to provide erosion mat and fully cover the expose soil . | Poor maintains of expose soil potential hazard silt water go public drain and can wash sheet water collecting. | Environmental
630 | Removed and stored at designated storage area | Unused water pump stored at edges. South plot-ECM 1 pond | Material storage
821 | Ask to remove the rebar | West plot , observed protruding rebar on the floor with out protection and Tripping hazard | Protruding Object
802 | Praised the workforce. | Confined space works in order at south plot 62-AD42. | Environmental
| Material storage area barricade rectify | West plot | material storage
511 | Instructed Amxon supervisor to elevate the cable at least 2m and above | Electrical cable elevated at low height along access at Entrance D | Electrical
321 | Ask contractor to Remove it from there to Relocate to Store | West plot, Observed diesel container and Unused vibrator left it near the scaffold access. | Access and egress
| Brief workers to check out tools before start work and follow up the monthly color code | TU6 area | electrical
370 | Installed the edge protection | No edge protection at south plot-V02, PTU. | Edge protection
926 | Identify body harness checked | Basin, 62AD45 | PPE
797 | Before start duct bank works must remove all water working areas . Ensure workers go in provide proper access for works . | Neste/ west plot/L76 Fw line | Access and Egress
330 | Housekeeping work | Site CTQ | Housekeeping
| Working area doing house keeping | West plot | housekeeping
182 |  | Proturding sharp edge object along the accessway, | Protruding object
813 | Brief workers to be mindful when working area is full of water ponding, pump out water first before godown the area | T42 south side | Environmental
| Material storage area barricading and house keeping | West plot | material storage
| Brief the worker to use proper hand gloves when using Electric Tools | Entrance E | ppe
312 | Immediately Temporary stop the pump operation until get Contractor to Arrange the another light for operation . | West plot , observed Tower light faulty at Concrete pump area for Night casting | Environmental
569 | Intervened to immediately placed localised noise barrier at noise source . | Zion - Havelock Road junction area hacking premix , generate noise pollution. | Environmental
902 | Arranged ecm slurry vacuum tanker to carry out water treatment maintenance. | Area 2 : water treatment plant overflow with silt. | Environmental
418 | Gcl PIC was informed and immediately rectified | Zone A poor housekeeping and material not keeping | Housekeeping
| Inform supervisor arrange cleaning after continue working | VS2 wall granite install work, on the scaffolding top working need cleaning materials form platform | housekeeping
579 | Informed pic of work and immediately provided | Failed to provide access for trenches opening | Access and egress
| Good practice Every day check temperature of workers twice a day to ensure safe health care | TU6 area | Health
185 | Generator no baricade, inform to them provide | 63AD05 | Electrical
| Tasked KTH Worker to place it at noise source with counterweight | Entrance C: Portable noise enclosure leaning against drain edge protection | edge protection
557 | inform amxon worker to do housekeeping | Ent. B | Housekeeping
| After work finish doing house keeping working area | West plot | housekeeping
150 | Instructed AMXON supervisor on site to relocate the purlins the soonest | Entrance B: stockpile of purlins blocking safe means of access | Access and egress
438 | User caution to bring adhesive in small quantity and to don face shield when handling it | Under pass: Hazardous adhesive left unattended | Hazardous substances
509 | Observed protruding hazard with rebar, remind and brief our supervisor need to cler immediately | Gate 12 - in front of HIA | Protruding Object
| Instructed Amxon subcontractor worker to revamp the fatal zone | Entrance A: MEWP counterweight out of fatal zone | fatal zone
| Safety time out conducted and instruct respective supervisor to comply fatal zone requirements | Ineffective of fatal zone managements and no banks-man present when carry out excavation works. Causes of serious injury when hit by excavator. South plot-62 AD 45, Basin | fatal zone
818 | Ask them to tidy up and Relocate to Storage area | Observed Material untidy at west plot R31 area | Material storage
30 |  | Gaps on the working platform, potential falling object hazard | Scaffold
852 | Advise team to lay the hose properly which lead tripping hazard. | Culvert 1/Center , | Access and Egress
872 | It was cleared and inform gcl Sup to make hole for drain water | Stagnant water Found at fire point station | Environmental
319 | Ask the contra to Protect or Remove . | West plot Protruding rebar without protection . | Protruding object
| Requested to be barricaded. | Entrance E Zone L to provide barricade on the uneven ground to avoid tripping hazzard. | edge protection
| Get the Contractor to Grounded night work Tower light . | West plot , Found Tower light’s Earth rod Not Grounded at J 11 area | electrical
425 | Instructed workers to do the protection | Admin building, protruding rebar to protect | Protruding object
178 |  | Improper top rail on the scaffold platform | Scaffold
78 | Instructed AMXON Supervisor to backfilled to same slab level and placed a steel plate on top of it | Entrance B: floor opening not fully backfilled for mewp movement | Floor protection
535 | Ask to cover temporary with nail it Display signage . | West plot , Last IC area not cover manhole cover , even though higher level from ground . | Floor Protection
292 | Brief workers to tidy up the storage area | T04 area | Material storage
180 |  | MEWP parked without adequate base steel plate | Supervision
| Get the Contractor clear immediately from there to Re- locate storage area. | West plot , Observed material kept it Edge of the Excavation area at R 31 | excavation
| Inform sub PIC to to arrange install zone signage for working area | Entrance E linkway slope install handrail not working zone signage for work | housekeeping
901 | KTH site supervisor notified to fix traffic reflective disc | Zion Road : Work zone may not be conspicuous to road users | Supervision
627 | Provided rebar protection | Provided rebar protection | Protruding object
551 | It was informed in the group to top up hardcore level to prevent stagnant water | Stagnant water at workers rest area | Environmental
| Arranged with Amxon site coordinator to rectify and instructed to stop using the scaffold until rectification done and approved by scaffold supervisor to use again | Ent-B underpass at lift lobby-mobile scaffold found with missing diagonal brace, toe board and inadequate outriggers. | scaffold
457 | Brief and request supervisor to provide protection for sharp edge | Ent C - Gate 3 - Foot path hoarding replacing | Protruding object
| Instructed him to wear mask correctly. | Worker wearing of mask incorrectly. Failed to comply COVID 19 measures. South plot-63 AD 05, Basin | ppe
508 | Arranged to reinstate | Gate 8 - StarHub utility marker being misplaced | Underground Utilities
776 | Falling items clear | West plot ECM | Falling object
733 | Instructed Amxon supervisor to provide adequate stopper to prevent any pinch point hazard | Toolsbox without proper stopper at station box | Material Storage
| Instructed workers to always observe social distancing | West Plot R31 area 2 | Health
250 | Silt fence repair | West Plot UG-04 | Environmental
| Ask the Contractor to Provided with valid FE and Updated Color code. | West plot , observed Tower Light Fire Extinguisher missing ? at K 01 area | fire hazard
933 | Lew sticker with out use it tools inform to them elec check and provide lew sticker | South, ptu | Electrical
857 | Arrange meeting with Kori and Lam Hwa safety site walk and get them clear asap prior proceeding any work that zone . | Sun-con : Kori & Lam Hwa , | Housekeeping
899 | Tasked Gammon supervisor to to reinstate the edge protection once the vibro hammer is relocated | GL7 Surface : Edge protection removed to allow vibro hammer excavator to be relocated | Edge protection
839 | Immediately ask worker to hang up about 2m | Culvert 2 center, cable was found lying on ground | Electrical
663 | Mobile crane fatal zone inter locking reinstated | West plot , P21-STR-1300 | Fatal Zone
9 | Tasked KTH supervisor to re align the edge protection | Entrance C: Edge protection not fully enclosing opening | Edge protection
670 | Ensure fatal zone barricades to machinery | C2 south | Fatal Zone
606 | Immediately get carpet combing team to tidy up shoe washing point, clear potential mosquitoes breeding ground | Site office - shoe washing point has been filled up with algae. | Environmental
| Ask the contractor to remove all balanced rebar & do housekeeping | West plot , observed balance Rebar and poor Housekeeping at Q81 area | housekeeping
942 | Arranged workforce to remove the grass. | Overgrowing of grass at south plot-T42, North | Environmental
971 | Instructed Multibase to hold back lifting operation. Gap to be filled with steel plates | Gl10/11: Crane outrigger pad packed with timber | Lifting
559 | Instructed AMXON fire watchman to either relocate the cable or cover them with fire blanket | Entrance D: Spark from overhead welding work in contact with cable | Fire hazard
254 | Provide soil protection | West Plot UG-14 | Environmental
351 | Instructed Amxon supervisor to inspect all water containers and clear out stagnant water. | Station box , observed water drum and containers collected stagnant water. | Environmental
92 | Get it Removed , instruct the contractor to Rearrange the cable to elevate level | West plot , observed Electrical cable on the ground along the Designated access | Electrical
345 | Intervened and brief to worker to cover face mask at all time . | East wall - observed worker not covered face mask | PPE
| Cleared stagnant water to prevent mosquitoes larvae breeding. | Found stagnant water underneath of generator dip tray. Potential of mosquitoes larvae breeding. 63 AD 05, Basin | environmental
973 | Intervened area inchagre to clear out stagnant water | Area 1 : Amxon material storage yard , collected stagnant water on canvas , beams compartment. | Environmental
745 | Raining sheet pile area hole , all area fill up done | T42, 62AD47 | Excavation
168 | Instructed supervisor to arrange metal scrap vendor to collect scrap bin . | Vent shart 2 surface, observed metal scrap bin overflow. | Environmental
442 | Instructed supervisor to seal up water barrier opening. | Area 2 : water barriers found wide opening, potential mosquitoes breeding ground | Environmental
949 | Immediately remove the canvas sheet and keep at storage. | Poor maintains of canvas sheet lead to water collecting potential mosquito breeding | Environmental
746 | Unwanted materials clear | T42, Ramp access | Material Storage
| Asked him to lower his tripod so theres no need to use platform. | South Plot , T42-PLT-104 | work at height
432 | Provided barricade at the entrance of the lift shaft | Platform GL8 Lift pit not barricaded. It will cause fall from height hazzard or fall at height objects hazzard on the worker inside the lift pit. | Falling object
576 | Installed edge protection and advised supervisor to present at all times. | No edge protection. Workers exposed to fall from height. No supervision by site supervisor. South plot-T42 Area 1 | Edge protection
904 | Immediately intervene and get banksman equipped with communication device | East wall - soil clearing works , banksman was not equipped with communication device | Excavation
240 | Unwanted scaffold items remove | West Plot last IC | Scaffold
827 | No proper access and edge barrigades provided while working below.Immediately arranged workers to make a access to go in. | west plot : J-11 area | Access and Egress
449 | No breeding were recorded at set up units. | Gravitrap - adult mosquitoes breeding surveillance units inspected | Environmental
167 | Instructed to supervisor to arrange scrap bin disposal from external vendor. | Traffic deck removal, scrap bin need to clear out regularly to avoid stagnant water. | Environmental
225 | Unwanted items clear | West Plot ECM/2 | Housekeeping
789 | Drain out tower light drip tray stagnant water | West plot P 21 SH 600 | Environmental
848 | Maintaining good fatal zone management | Culvert 2 South | Fatal Zone
261 | Apply slope protection | West Plot UG/04 | Environmental
293 | Brief workers to maintain safe distance while working | T04 area | Environmental
601 | Instructed supervisor to store all pvc materials 300mm above the ground | Ent D pvc pipe store , elbow materials stored on ground, potential mosquitoes breeding ground | Environmental
485 | Told the contractor to lock it and display necessary Signages . Strictly inform them to Comply always | West plot , Observed Generator enclosure door was not locked and Insufficient warning signage | Electrical
415 | The team was remind and stopped the work without PTW for piling rig and get them to complete and approved sign to resume | ll gems Failed to done the PTW checklist before start work | Supervision
584 | Instructed workers to put in red barriers ASAP | Technical building, excavator without fatal zone/red barriers | Fatal zone
640 | Instruct supervisor to replace the sticker | Fire extinguisher service inspection date has disappeared. West plot-STR 800 | Fire hazard
226 | Obstruction items remove from walk way | West Plot ECM/2 | Access and egress
| Ask the contractor to provided Temporary barricade.. | West plot , Rebar Even to be use today also kept it on the ground and No barricaded at STR 300 | protruding object
44 | Deployed additional workers | No buddy system. Worker carry out manual excavation without buddy system and supervisor. South plot-T01 | Excavation
| Those identified water receptacles has been placed sabd granular abates to control mosquitoes breeding. | Fortnightly sand granular abate- mosquitoes control inspection carried out. | environmental
636 | Very poor Housekeeping. Ask respective contractors to do housekeeping immediately | P21 str 1300 west plot | Housekeeping
| inform amxon's subcon to lift up cable wire | entrance E poor cable management | electrical
| Good practice Genset fully covered with barricade and display signs provided | W63 area | electrical
22 |  | Overgrown vegetation along hoarding area, potential mosquito breeding ground. | Environmental
| Hazard rectification : Protruding rebars along side the working area vertically, which may cause the workers to hit/scratch while walking. so immediately ask the supervisor to put the end caps at the rebar. | West plot : N-51 | protruding object
| Informed electrician to rectify to prevent any electrocution | Extension cable junction box cover missing at concourse level | electrical
550 | It was informed team to reroute and make it hang up above ground 2m | Poor cable management at site access point | Electrical
439 | Gammon Supervisor notified to extend the edge protection the soonest | VS2: Incomplete edge protection | Edge protection
| Instruct respective supervisor to inspect the PPE daily without fail. | Good practice: PPE inspection was conducted before usage of safety and other necessary items. South plot-63 AD 05 , Basin | supervision
| Kth notified to backfilled the trench expeditiously | Entrance A: Trench for drain construction occupying space | access and egress
| Immediately arrange the man put the cone& cap filled the sand and grouted. | GL4 pedestrian Walk way premix cracked. | access and egress
596 | Algae grown on footpath. | Linkway to blk 94 Havelock Road | Environmental
858 | Stop Zhao Yang work and advise them to store material proper barricades with signages . Some chemical material mix with composites material which immediately clear . | Sun-con: Zhao Yang, | Material storage
74 | Inform sub PIC to arrange any time must close gate | VS2 gate 3 small gate not close, public maybe can going | Security
437 | Tasked yongnam supervisor to fix missing edge protection the soonest | Surface Level: Access to workplace with missing edge protection | Edge protection
| Instructed Gammon supervisor to cut the reinforcement steel and remove the mud expeditiously | GL9: Access obstructed by reinforcement steel and filled with mud | environmental
222 | Good practice, apply mosquito oil routine basis | West Plot | Environmental
311 | Ask the Lifting team to Secured properly . | West plot , observed precast support Wire rope Clamp secured wrong method | Lifting
961 | Informed to pic clear the unwanted materials prevent to Trip& falling hazards | Entrance B ,poor house keeping, people may get Trip & falling hazards &fire hazards. | Housekeeping
662 | Tower light barricaded & provide the existnguisher | West plot , P21-STR-1300 | Fire Hazard
817 | Red barrier is useful for moving machines to barricade, not cover up of barricade | X01 area | Fatal Zone
918 | Arranged with Baskar to reinstate | MHS2A-edge barricade are the caisson edge fell on the floor | Edge Protection
689 | Informed Supervisor to Ensure no water ponding within excavated area. | Culvert 2 South | Environmental
688 | Informed Supervisor to Ensure the barricades at edge of ERSS are stable. | Culvert 2 South | Edge protection
| Advised scaffold supervisor to update accordingly | The letters have disappeared on the scaffold tag. Unable to read. South plot-63 AD 05, Basin | scaffold
11 | Tasked GAMMON Supervisor to remove them | Zion Road: Protruding bolt on the concrete barriers | Protruding object
| Access no have, inform to them provide | PTU, west | access and egress
983 | Inform Otis project engineer swc to tidy up the cable .to avoid tripping hazard | Upper concouse | Access and Egress
317 | Ask the contractor to Relocate the light | West plot , Tower light observed Unbalance due To heavy rain | Environmental
982 | Instructed area supervisor to cover cement bags pallet and not in use drum clear out. | Platform area stored cement bags and water drum unattended, potential dust pollution & poor maintenance | Environmental
| Ask the Contractor to Provided end protection . | West plot , Found Rebar end Protection missing in the Spun pile Rebar . | protruding object
1004 | It was informed GCL Sup to closed immediately | Construct worker rest area found none protected protruding rebar | Protruding Object
| Inform the supervisor to put hard barricate to the cable trench opening | West plot | edge protection
869 | Informed gcl Sup to get it safety sign and blocked access | Paintshop roof access failed to close when unattended | Supervision
| Remind banks-man to use mobile at rest area only. Mobile allowed to use only frontline staffs to communicate job related and also their should be stand at safe place or rest area. Remind operator to keep materials inside the bucket only. Make sure not overflow. | Banks-man was using mobile at site and walking along the vehicle access. Materials is overflow from bobcot bucket and fall down some of the items. South plot-T01 | supervision
215 | Good practice, mosquito oiling in rutine basis | West Plot | Environmental
219 | Good practice, ECM monitoring in rutine basis | West Plot | Environmental
650 | Get it Fix back the Barricade . | Observed pit edge barricade was removed by other contractor and Not reinstate the barrier | Edge protection
| Protruding rebar cap missing. Ask respective contractors to provide barricade immediately | P21 compressor | protruding object
673 | Scaffold supervisor reprimanded to monitor his workers safety performance. Horizontal scaffold tubes shall be fixed first at 1m height for them to hook up the harness | Entrance B: Incorrect method to hook up safety harness | Work at height
577 | Reinstate hard barricade | Opening on excavation area. South plot | Excavation
| Updated team identification number | No clear of team identification number. Possibility to mix the team. South plot-T01 | supervision
181 |  | No provision of fire blanket / protection for escalator during hot works at near escalator | Fire hazard
199 | Reminded banksman to provide red barricades | No provided fatal zone barricades. South plot-V12 PTU | Fatal zone
196 | Informed respective supervisor to reinstate the slope protection. | Ineffective of slope protection. South plot-PLT108 | Excavation
677 | Instructed Sam Lain supervisor to modify the edge protection to cater for the gap /opening | GL15 : Opening not sufficiently barricaded | Edge protection
736 | GI hang the elec wires, use S hook | Ptu | Electrical
| Deployed workers to remove soil from drain | The permitter drain is blocking with soil. The water will not able to flow freely. There is obstructions. South plot-T42, Retaining wall ramp area | environmental
910 |  | Traffic diversion hacking existing premix generated noise pollution and localised noise barrier were placed away from the noise source. | Environmental
774 | Clean stagnant water prevent mosquito briding | West plot | Environmental
326 | Immediately report and briefing gammon PIC and drill gems supervisor to provide proper base plate. | Zone B drill gems No provide proper base plate and cement tank stand. Potential hazard when you load may lead to topple . | Falling object
| Rebar storage area barricade and house keeping | West plot | material storage
270 | Told the respective sub con not to leave safety harness attended | West plot P 21 | PPE
| Get the civil contractor to Clear unwanted material ... | West plot , observed poor Housekeeping at N 51 area | housekeeping
336 | Tasked nearby worker to fix back the top rail immediately | Entrance B: Edge protection top rail displaced | Edge protection
342 | Instructed supervisor to clean up diverted public area. | Along zion road diverted public walkway observed loose soil and dry leafs. | Housekeeping
| Drained out the towerlight drip tray stagnant water | West Plot J 11 | environmental
398 | Ask the contractor to Extern the Additional one more rail to rise up . | West plot ,Scaffold top rail too Low from the Rebar Level . | Scaffold
917 | Works are not allowed in this platform, Arranged with Amxon to get the scaffold supervisor to check and endorse | Ent B High void scaffold found with expired scaffold tag | Scaffold
121 | Drilling location need to backfill sands. Subcon: ZYG | South culvert 2 | Excavation
105 | Instructed supervisor to pump out ponding water. | Gate 3 : roofslab area collected ponding water, potential mosquitoes breeding ground | Environmental
86 |  | bared slope area not covered properly, which causes soil erosion ( water pollution) | Environmental
709 | Informed to traffic controller fix the reflective disk | GL13-15 Water barrier missing to reflective disk. | Environmental
| Tasked KTH to assist and reinstate the edge protection | Entrance C: Edge protection removed by party | edge protection
| Instructed Gammon site electrician to slot in the exposed cable into DB enclosure or effectively cover with insulation tape | GL9 surface: Exposed cable | electrical
390 | Ask the contractor to clean the area . To prevent Slippery hazard. | West plot , observed Generator area very muddy . | Access and egress
878 | Instructed Chuan Lin to clear the debris & to locate to one area with barricade instead of leaving it at multiple location obstructing the access way | Technical Building - hacked rc pile debris with protruding rebar was place at common access way area | Access and Egress
| Good practice. Workers maintain safe distance while working | Tu3 area | Health
| Remind them to comply all the work area sufficient lighting for night work | West plot, observed Provided sufficient lighting for Night work | general lighting
401 | Told contractor and check and update the check list before use . | West plot Observed , Air compressor not check and update check list | Supervision
654 | Strictly ask them to close / lock and Comply the with full Electrical requirements | West plot Observed Generator fencing Gate Not Locked | Electrical
198 | Provided metal planks to walk | No metal planks on the rebar slabs to walk. Could causes of injury when trip and fall. South plot-62AD05 | Access and egress
| Get the contractor to provide the Rebar protection. | West plot , Found protruding Sharp Rebar without protection at N 51 | protruding object
| Over head no protection | Ent A rooftop | falling object
266 | Stop the work and ask them to provide protection of bolt before they can resume backfilling. | T42-PLT-108 (Backfilling) | Excavation
238 | Apply soil protection | West Plot L/03 | Environmental
| Disposed abrasive wheel, remind with subcon management to procure approved abrasive wheel. | Use of non-approved brand of abrasive wheel on site at West Plot. | power tools
284 |  | P21 SHT 100 fatal zone barricade ( good practice) | Fatal zone
555 | lnform supervisor to housekeeping | Ent G ground level need to housekeeping | Housekeeping
228 | Obstruction item remove from access area | West Plot ECM/3 | Access and egress
| Informed respective contractor to install rigid barricades | No fall protection at trench opening. Potential of falling hazards. South plot-T01 | edge protection
704 | Instructed gpl sup to relocate or to utilise the gi pipe for erection to demarcate gol work area between other contractor | Bromine building - improper housekeeping, scaffold material left in a haphazard manner | Housekeeping
| Informed SWC to stack/store their materials properly and stable. | Ent E Underpass | material storage
151 | Notified GAMMON site electrician to rectify the defect the soonest | Entrance D: Electrical junction with internal cable exposed | Electrical
| Identified those potential mosquitoes breeding ground and applied larvaciding | Weekly engaged pest control service carried out at site | environmental
567 | Protruding joint had been protected with plastic cover | Havelock Road, diverted public walkway protruding railling joint may hurt to passerby public | Environmental
| The workers working without keeping the permit and MSRA at the worklocation. Instructed to place all documents at the work place | 63PK 03 | housekeeping
928 | All the scaffolding vertical pipe use missing tape close it, prevent mosquito breeding. | South plot all | Environmental
57 |  | Unattended / no labelled chemical drum stored with RC drain. | Hazardous substances
131 | Briefing to provide barricade | Sharp edge no protect ... no barricade potential hazard. | Protruding object
| Instruct rigger man to get worker to hold the platform ladder when using it. | No buddy system when climbing up on the platform ladder. Possibility to get injury when slip and fall from ladder. South plot-63 AD 05, Basin | work at height
470 | Installed edge protection | Missing of edge protection. Potential of falling hazard. South plot-V12 PTU | Edge Protection
| Scaffolding platform not put hand rail and put safe tag | S77 | scaffold
| Instructed AMXON to dispose it the soonest | Entrance B: shattered glass | Housekeeping
87 |  | before commencing traffic deck hacking need to provide localised noise barriers | Environmental
959 | infrom to supervisor doing proper hung the cable | Ent G Extention cable laid onthe floor | Electrical
243 | Stagenant water clear | West Plot last IC | Environmental
128 | Confined space work start before gas check based 3 layers | South culvert2 | Supervision
628 | Removed from walkway | Sunny hose are laying on the walkway. Could causes of serious injury when trip and fall. South plot-T01 | Access and egress
252 | No use items remove from work location | West Plot UG-08 | Housekeeping
399 | Ask the Sub contractor to Fully fenced around Generator . | West plot area Generator area not fully fenced . | Electrical
| Brief workers to maintain safe distance while working to ensure health care | TU4 area | Health
| Inform the respective supervisor incharge to fix missing whip arrestor and rectify the blow pipe handle | West Plot Q66 | power tools
| Good practice Check temperature of workers twice a day to ensure health care | TU4 area | Health
536 | Ask to stop use and get it inspect by Their LEW with sticker then use on site | West plot , observed Electrical Hilti breaker Without LEW inspection sticker | Hand Tools
| Identified those water ponding areas and applied larvaciding treatment. | Weekly pest control service carried out. | environmental
507 | Arranged to install new railing along the road | Ent D - Footpath found without hard barricade next to the new road | Edge Protection
| Infirm the respective sub con to provide hard bsrricate to the manhole opening | West Plit P 21 | floor protection
| Inform the respective sub con scaffolding supervisior to verify the scaffolding access and egress if ok provide the missing scaffolding tag | West Plot R 31 | scaffold
837 | Informed to pic make 300mm high rake Make & storaged. | GL11-12 pvc pipe not properly storage. | Material storage
1000 | Removed and clear | Poor maintains housekeeping the materials collecting water potential mosquito breeding | Housekeeping
761 | Damage LG remove from site | West plot R31 | Lifting
| Report to PIC that materials clear immediately keep in the proper storage | L angle brackets are laying on the scaffold that was not secure and blocking main entrance access . | access and egress
| Barricading the material storage area | West plot | material storage
896 | Tasked KTH worker to expand the fatal to suit the slewing zone | GL 7-10: Fatal zone is narrow for plant to swing without going over the barricade | Fatal zone
978 | Immediately get area inchagre to carry out housekeeping | Entrance E - material storage on floor area collected stagnant water. | Environmental
| Good practice. Workers maintain safe distance when working | TU6 area | Health
587 | Instructed GPL sup to install scaffold access platform or put temporary sand bag at the access area | Improper access to pile cut off area. Potential trip & fall hazard | Access and egress
847 | Poor lighting to work shotcrete pump operator Action: arrange proper lighting workplace. | South culvert2 | Environmental
486 | Told the Contractor to Replace the Fire Extinguisher | West plot , observed Tower light without Fire Extinguisher at R31 area | Fire Hazard
| Instructed AMXON Supervisor to cushion these sharp edges expeditiously as this access is used extensively by workforce | Entrance E: Incomplete balustrade with exposed sharp edges | protruding object
| Ask the contractor to provided immediately | West plot , Rebar Protruding without any Protection at N 51 area | protruding object
46 | Provided fire extinguisher | No provision of fire extinguisher while carry out hot works. South plot-T42, Section 4 | Fire hazard
| Request contractor remove pvc pipe immediately to prevent mosquito breedig | Ent B - gate 8 - surface level | environmental
| Removed unwanted concrete test cubes. Remind respective contractor to maintain good housekeeping at site | And other SDM practices. | housekeeping
| Remind and brief technician on hanging power cable 2m from ground | Surface - gate 2a | electrical
469 | Shifted the materials and stock piles as per PE design. | Materials at edge of excavation and stock pile to be 4m away from excavation as per PE design. South plot-62AD05 | Excavation
734 | Granite kept on edge of scaffold platform during installation works, it should keep on the centre of the platform | Entrance B | Falling object
53 | Informed respective contractor to pump out the water to prevent mosquitoes larvae breeding. | Stagnant water along the cable trenches due to heavy rain. South plot-V12, PTU area | Environmental
980 | Intervened and get team to collect all empty cement bags to collect and dispose safely. | Gate 6 floor screeding works, empty cement bags scattered all around. | Housekeeping
719 | Tasked and instruct KTH to create an access due to different ground level | GL9 surface : No safe means of access and egress | Access and egress
| Footing edge barricade missing. Ask them to arrange edge barricade before going up. | P21 PR 500 shallow foundation | edge protection
732 | Instructed Amxon supervisor to clear the materials from the access and maintain the access free from any obstruction | Materials stored on the staircase access at station box area | Access and egress
950 | Both supervisors remind and arranged banksman immediately and guide | Failed to provide banksman for guide Cape and Hi-Tact lorry at main entrance | Supervision
726 | Work stopped and briefed to the Amxon scaffold sup to rectify | Station Underpass at ent A- mobile scaffold found with unapproved access modification. | Scaffold
| Brief workers to follow the monthly color code for the hand tools | TU4 area | electrical
| Good practices : spraying of curing compound after casting to strengthen and avoid having cracks on the surface. | West plot : Q81-PR-200 and 66FA-01 | supervision
366 | Removed the materials from edges. Advised contractors to store materials 1m away from edges. | Materials stored at slopes. South plot-PLD108, | Material storage
841 | Ensure to display in the tally board and get registered before going down in confined space | C1 south | Supervision
| Installed rigid hard barricades to prevent people from falling hazards. | No hard barricades at tench opening. Potential of falling hazards. South plot-T01 | edge protection
676 | Cautioned them to be on the look out for vehicle from Zion Road entering Holiday Inn slip road | GL1: Hoarding work | Supervision
820 | Ask to Tidy up the area and Clear all unwanted material . | West plot , K 71 area Housekeeping and Tidy up the area | Material storage
641 | Informed subcontractor supervisor to stack the materials at least 300mm above from the ground. Ensure remove the unwanted materials from site. | Formwork materials are left at site unattended. Stacked direct on the ground. West plot-STR 800 | Material storage
696 | LS was informed and get it immediately | Failed to done Lm&LG monthly color code for lorry crane used | Lifting
565 | Arrange with person inchagre to clear out stagnant water. | Covent Garden, metal beams storage collected stagnant water. | Environmental
844 | No update monthly colour code for Tower light Subcontractor: lam hwa | South culvert 1 | Electrical
96 | Get the contractor to Clear / disposed to waste bin | West plot , Observed Unwanted material left it on the ground Poor Housekeeping | Housekeeping
603 | Instructed Amxon team to backfill depression area with soil | Entrance E : external surface depression areas collected stagnant water. | Environmental
| Ask the Excavation contractor to provide slope protection fully | West plot, Observed slope protection not fully covered at Q 81 area | excavation
| Mobile parking safe distance from excavation slop & provide proper barricade...with interlock | South plot W 03 | excavation
800 | Water all clear duct bank areas before start works . Check the near by activities & make barricade properly your working areas | Neste/West plot/P21 Str 100 | Housekeeping
| Cleared unwanted materials | Poor housekeeping. Failed to tidy up the areas. Unwanted materials left at site unattended. South plot-W03 | housekeeping
| Inform sub supervisor to arrange, must installation rebar protect | Entrance E link way to taxi bay wall rebar not protect, can hit workers | protruding object
| Protected the protruding rebars by metal zinc trough | No protect the protruding rebars. South plot-63 AD 05, Basin. Unguarded protruding steel reinforcing bars are hazardous. Even if you just stumble onto unguarded rebar you could impale yourself, resulting in serious internal injuries or death. Various accidents involving impalement due to unprotected rebar commonly occur in the construction industry across the globe. | protruding object
981 | Instructed to supervisor turn over metal casin storage to avoid stagnant water collection | Gate 12 : manhole cover metal casing compartment collected stagnant water | Environmental
948 | Reprimanded Subcon Supervisor and Banksman to implement proper fatal zone management barricades. | Zone F Subcon Hi-Tact, misuse of yellow barricades for fatal zone management. | Fatal Zone
880 | Instructed Chuan Lin to always managed the hose layout so as not to cause potential obstruction. To relocate the hose to one side whenever change of hacking pule area | Technical Building- poor air compressor hose management. Potential tripping hazard on the so called accessway. | Housekeeping
162 | Set up maintained well and no breeding recorded. | On site gravitrap- adult mosquitoes surveillance set up inspection carried out | Environmental
373 | Protected of protruding rebars using by metal planks. | No protect the protruding rebars. South plot-T01 | Protruding object
| Inform the contractor to Remove to Re-locate to store area and Housekeeping | West plot , observed material untidy / Poor housekeeping atJ 11 area . | housekeeping
59 |  | Materials over stacked, potential falling object hazard | Falling object
806 | The spun pile head not covered by plywood and sand bag. Ask people to cove the spun pile head with plywood and sand bag immediately. | West plot P21-Compressor shelter | Floor Protection
830 | Rebar protection cap missing and put it back | South plot | Protruding Object
| Get the contractor to Rectify immediately , cover and Secured fully | West plot , Generator fencing with opening at P 21 area | electrical
897 | Tasked KTH supervisor to cover the exposed rebars with trough | GL4 : Rebar without protection | Protruding object
608 |  | Improper fatal zone management and lifting supervisor not present while hoisting works | Fatal zone
242 | Stagenant water clear and housekeeping | West Plot last IC | Environmental
828 | Missing of sand bags on some of the spun pile heads.Ensure the worker to put the sand bags on the pile head. | West plot : R-31-SHT-100 | Floor Protection
| Instructed kth Supervisor to follow up the soonest | Entrance C: Exposed rebar without protection | protruding object
| Remind respective contractor to tidy up and removed unused materials | Poor housekeeping: Formwork materials are not clear after dismantled work completed. South plot-S01 | housekeeping
711 | Informed electrician to install pvc pipe to prevent any damage and electrical shock | Entrance E lighting live wire without protection | Electrical
| Didn't provide hard barricade, tripping hazard | Covent garden | access and egress
200 | Provided walkie talkie | No provided walkie talkie to banks-man for guide excavator operator. Failed to comply gammon bold commitments. South plot-PLT 108 | Excavation
541 | Ask them to Remove Since not use / unprotected | West plot Observed Protruding support rebar on the Floor without Protection | Protruding Object
| Tasked AMXON Supervisor to monitor the work closely. Banksman to focus on the assigned job | GLSA3: 2 plant working within close proximity | fatal zone
940 | Sealed up the G.I pipes to prevent larvae mosquitoes | No seal up the vertical G.I pipes. Potential of larvae mosquitoes breeding. South plot-U52 | Environmental
| Instructed Amxon scaffolders to fix the handrails immediately because they are at risk | Entrance A planter box: Scaffold under construction step ladders without handrails | scaffold
| Suggest to Gammon supervisor to consider installing another access | GL6/7 surface: Demolition of capping beam encroaching the access | access and egress
62 | Immediately repot drill gems Suppervisor to provide safety whiplash. | Drill gems Zone B Grouting hose no provide safety whiplash lead to potential hazard | Power tools
| Work monetarily stopped. To use bracing of equal length ,refrain from extending working platform to gain height and to apply wheel choke. Scaffold Supervisor to reinspect the scaffold | Entrance A: Unstable mobille scaffold | scaffold
36 | Rebar no protection, inform to Sup protection | Retaining wall area 4 | Protruding object
506 | Clear water and provide canvas sheet properly | Pounding water on the canvas sheet at BLK 93 junction | Environmental
| Stopped the unsafe act. Briefing to the workforce. Informed scaffold supervisor to modify the scaffold platforms | Unsafe act: Worker was standing on top of the G.I pipe fo tying rebars due to insufficient height to reach rebar level. South plot-63 AD 05, Basin | scaffold
| Reinstated the Fatal Zone for Vibro machne | West plot , L76 , 61AD-42 Basin Area | fatal zone
607 | immediately close Hoardings after close | Hoarding open ready Sharp edges near public footpath | Protruding object
840 | Maintain human eccess | C1 south | Access and Egress
946 | Instructed Subcon Supervisor to fix back and use the grinder with the handle. | Zone C Subcon Cape, use of handheld grinder with missing handle. | Power tools
454 | Instructed to operator for activate water treatment plant. | Station box roof slab collected ponding water. | Environmental
537 | Ask the contractor to provide Slope protection | West plot , Observed Excavated area insufficient slope protection . | Excavation
| Barricaded the crane surrounding with red barriers | Failed to cordon of the crane by red barriers. South plot-62 AD 05 Basin | fatal zone
271 | Drained the tower light drip tray stagnant water | West plot P 21 STR 600 | Environmental
| Ask contractor to Replace the Fire Extinguisher with good condition. | West plot , Found Fire Extinguisher pressure gauge needle turn to Red zone ( de-pressurised ) | fire hazard
114 | Advised worker to wear proper pant | Found worker wearing of track pant at work place. South plot-V12, PTU | PPE
883 | I told to safety to clear the stagnant water in entrance B ground level | Entrance B Ground level stagnant water on the ground can cause of mosquito breeding | Environmental
6 | Tasked AMXON lifting Supervisor to shift the hoarding if need to or review the slewing path | Entrance A/ Block 94: Hoarding panel too close to mobile crane counterweight | Lifting
810 | Brief workers to stack materials properly to ensure lifting time no slips | T42 North | Lifting
| Ladder heights no follow scaffolding act, inform to them follow it. | T42, area 04 | scaffold
| Cement mixer machine no LEW inspection for this month | Entrance B | electrical
360 | Advised worker to wear | Failed to wear hand gloves while carry out drilling works. Could causes of hand injury. South plot-T42 Retaining wall ramp area. | PPE
667 | Ensure no obstruction at access way | C2 South | Access and egress
| Ask the contractor to provided the mid rail . | West plot , Observed hard barricade missing mid rail for Pit area | edge protection
368 | Provided banks-man | No banks-man present for the moving machinery. Could causes of serious injury when hit by machinery. South plot-V11,PTU | Fatal zone
748 | Generator plug smoke, inform to electrician change. | T42, south, retaining wall | Environmental
965 | Informed to pic make 300mm high rake Make & storaged. | GL11-12 pvc pipe not properly storage. | Material Storage
727 | Remind, briefing and request safety to follow up for cable hanging. Important, cable must be cleared not inside fatal zone of machine | Ent B - Apron slab GL EB1 - 5 | Electrical
615 | All area clear unwanted materials | South plot | Housekeeping
| Good practices : All protruding rebars are provided with the rebar end caps to avoid injuries to the workers. | West plot : N-51 | protruding object
758 | Stand down was conducted to the lifting crew to comply the requirements. | Travelling excavator while lifting of trench. | Lifting
566 | PIC arranged localised noise barrier close to noise source of machinary to reduce noise level. | East wall surface area , traffic diversion prepration works , premix paving job generates noise. | Environmental
| Ask the contractor to do Housekeeping | West plot , observed poor Housekeeping at Plywood cutting area at N 51 | housekeeping
| Time out the Excavator vibro and ask the Contractor to Extend the Red Barrier and Swinging area keep clear | West plot , observed Excavator Vibro’s counter weight out of red barrier /swinging area must be Clear with Red-barricaded. | fatal zone
665 | Clear water from dip tray | C1 south | Environmental
| Protruding rebar cap missing and rectify immediate to prevent incident & accident | South plot | protruding object
625 | Removed the unwanted materials from site | Poor housekeeping. South plot-P02 | Housekeeping
| Tasked Gammon supervisor to suspend it at least 2m above ground | Entrance: A: Electrical not sufficiently suspended | electrical
396 | Get the Contractor to Remove it immediately | West plot , observed unwanted timber’s with nail along the access | Protruding object
| Get the Contractor To provided the Barricaded fully . | West plot , Observed Rebar storage area not Barricaded fully | material storage
724 | infrom to supervisor and close opening immediately After close | Floor opening no barricades or no proper cover. worker walking time lege can get injury | Floor protection
| Suggest to Amxon Supervisor to dismantle and replaced with tube and fitting | Entrance B: Mobile scaffold with missing safety components | scaffold
723 | Engaged NEA authorities pest controller to carry out chemical misting service at TLQ'S | TLQ'S arranged indoor residual fogging , to prevent from adult mosquitoes | Environmental
355 |  | Gas cutting works carried out without adequate fire blanket provision for spark containment | Fire hazard
77 | Amxon Supervisor notified to modify the barricade to cater for access | Entrance B: Access blocked by hard barricade | Access and egress
127 | Culvert 2 Human accessway crane boom parking its consider line of fire. | South culvert2 | Fatal zone
| Inform subcontractor to improve house keeping. | Ent B Below escalator poor house keeping and fire hazardous. | housekeeping
| Briefed respective contractor about importance of red barriers and usage. | Cordon off the machinery using by yellow barriers. Failed to comply gammon bold commitments. South plot-W03 | fatal zone
632 | Briefing was conducted to the workforce. Advised to provide access before enter into Excavation pit. | Worker enter to excavation without any safe means of access /egress. No supervisor available-South plot,X71 | Access and egress
| Informed electrician to check and rectify | It was found ventilation fan cable exposed at concourse level | electrical
| Notified and instruct AMXON Supervisor to remove debris the soonest which may fall when workers are doing rebar work | Entrance E: Loose debris along excavation trench | excavation
259 | Sharp nailed formwork remove from access area | West Plot UG/04 | Protruding object
| Brief workers to drink more water in hot weather conditions | TU4 area | Health
| Instructed AMXON subcontractor Supervisor to reinstate the edge protection including the temporary drain cover | Entrance B: Edge protection were removed to facilitate floor screeding work | edge protection
236 | Unwanted scaffold pipe remove and prevent falling object | West Plot L/03 | Scaffold
| Advice to all Use it properly and Wash it Regularly . Which is water Repellent 50 washing thus mask . | West plot , Observed Technip Issue to all Reusable 3-ply Fabric face mask. | ppe
938 | Provide man power to make access and brief | U52 | Access and Egress
| Inform the respective sub con supervisor incharge to provide barricate. and signage | West Plot J 11 | edge protection
| Excavation done without fatal zone barricade. Instructed the workers and supervisor to strictly comply with the fatal zone barricade. | 63PK 05 | fatal zone
683 | Action: stop activities , briefing the teams provide Fatal zone barriers & banks man | South culvert 1 | Fatal Zone
156 | Instructed supervisor to arrange drain cleaning to avoid stagnant water. | Along kim seng road drain inside observed stagnant water and algae formation. | Environmental
234 | No use rebar clear and remove tripping hazard | West Plot K/71 | Housekeeping
546 | Immediately stop and briefing to wear face shield. | Using Pipe cutter machine worker no wear face shield lead to potential hazard . | PPE
183 |  | Scaffild access was not checked and updated by scaffold supervisor | Scaffold
| Inform scaffold supervisor immediately rectify | Ent,A finding toe board missing | scaffold
| No provide toeboard material can be faill from height | concourse level Gl 11 | falling object
693 | Briefing to clear immediately... | Cable storage canvas sheet collecting water potential mosquito breeding @ near pant shop . | Environmental
586 | Instructed Chuan Lim to clear the left over debris & to arrange future debris in a safe manner | Administration building- Hacked debris from the rc piles was left adjacent to designated access way | Housekeeping
| Backwash water treatment plant and top up chemical dosing tanks to ensure water treatment available for rainy peroid. | Ent E: Earth control measures maintenance carried out. | environmental
464 | Updated tag and color code | Failed to update monthly color code and missing of tag for the forklift. South plot-62AD05, Basin | Lifting