## Sheet1
S/N | Immediate Actions Taken | Short Event Description | Classification
653 | Ask to Get it install mid rail then allow them to proceed work . | Observed west plot R31 area footing rebar slab provided barricade all side but missing mid rail . | Edge protection
994 | Block walking access at underpass during working time When people walking from the access at may be caused tripping hazard , need provide proper barricade | Entrance E underpass | Access and Egress
627 | Provided rebar protection | Provided rebar protection | Protruding object
12 |  | Damaged safety shoe with holes and collected water. | PPE
67 | Informed pic top up the cement prevent people Trip& falling hazards | Blk 94 bus stop uneven surface | Access and egress
267 | Advise the worker not to carry hands told on the shoulder when he turn possible hit other people | West plot container lay down area | Manual handling
327 | It was remind drill gems to provide proper stopper and support to prevent self rolling | Improper material storage without stopper for pile casing | Material storage
287 |  | R31 STR 100 reactor access scaffolding good practice | Scaffold
955 | Instructed Chuan Lin to provide designated access point for worker to access to cut off pile area to prevent potential tripping hazard due to ground position. Chuan Lin informed that the access egress is not under their work scope. Chuan Lin informed that GPL must provide | Admin Building - inadequate & improper access towards rc cut off piles location | Access and Egress
368 | Provided banks-man | No banks-man present for the moving machinery. Could causes of serious injury when hit by machinery. South plot-V11,PTU | Fatal zone
380 | Removed items and stored at designated storage area. | Materials are not stack properly. | Material storage
423 | Briefing done. Smoking allowed only inside the designated area. | Smoking inside the site boundary. | Fire hazard
465 | Updated the color code by lifting crew. | Failed to update monthly color for webbing sling. South plot-T42, Retaining wall ramp area. | Lifting
212 | Earthing rod was installed properly and provided barricades. | Tower Light without proper grounding, ACB left open and barricades. South plot-PLT108 | electrical
407 | Stop the welding work and ask welder to do replace the it earth clamp | West plot observed Welding earth clamp secured with Binding wire . | Electrical
117 | Expiry LG can't use on site Subcontractor:ZYG | South culvert 1 | Lifting
783 | Damage items clear from work location | West plot N51 | Housekeeping
927 | Dirty, inform to our worker sweep it | Canteen at south | Housekeeping
498 | Discussed with GAMMON site agent and suggest constructing a ramp | Holiday Inn: Temporary sewer line obstructing public access | Underground Utilities
27 |  | Protruding rebars observed without protection. | Protruding object
747 | Genset lew sticker provide | T42, retaining wall | Electrical
915 | Inform to Amxon sup to barricade to avoid tripping hazard | Platform level | Access and Egress
877 | Good practise | Technical Building - Adequate steel plate in placed for the mobile crane & fatal zone in placed (maintained) throughout the lifting operation | Lifting
719 | Tasked and instruct KTH to create an access due to different ground level | GL9 surface : No safe means of access and egress | Access and egress
382 | Informed gammon direct respective supervisor to arrange the materials properly. | Poor housekeeping: Scaffold materials are not stack properly. Placed direct on the ground. South plot-62AD45, Basin | Housekeeping
236 | Unwanted scaffold pipe remove and prevent falling object | West Plot L/03 | Scaffold
451 | Instructed supervisor to arrange spraying water for dust compaction. | Opposite blk 94 , hacking concrete slab generated dust pollution | Environmental
511 | Instructed Amxon supervisor to elevate the cable at least 2m and above | Electrical cable elevated at low height along access at Entrance D | Electrical
408 | Immediately ask them to bring back to store . Don’t use until LEW inspection with sticker . | West plot, observed Electrical Extension cable without LEW sticker . | Electrical
509 | Observed protruding hazard with rebar, remind and brief our supervisor need to cler immediately | Gate 12 - in front of HIA | Protruding Object
784 | Change lifting belt | West plot, pipe rack | Lifting
146 | Informed subcontractor to replace it to prevent any electrocution | Damage extension cable socket outlet at entrance B | Electrical
531 | Access closed to stop usage | This green card access is not safe. Could causes of injury when slip and fall. South plot-T42, Ramp access | Access and egress
554 | Instructed GPL Yeasin to clear the debris & to allocate to one area instead of leaving it behind scattering | Admin Building- observed left over balance debris from cut off rc piles along the common access way although majority of the debris had been cleared. | Access and egress
921 | didn't provide fire blaked during welding have informed to provide fire blanket. Fire sparks dropping down | Entrance D | Fire hazard
608 |  | Improper fatal zone management and lifting supervisor not present while hoisting works | Fatal zone
624 | Instructed worker to wear face mask. Make sure wear the mask at all times except eating or drinking. | No wearing of face mask. Failed to comply covid 19 measures. South plot-T42 | PPE
637 | Carried out house keeping at this area and cleared the material from walkway. | Access is obstructed by rebars. Causes of trip and fall. West plot-R31. | Access and Egress
328 | Gcl PIC informed to put up necessary barricade | Zone H failed to provide rigid barricade for Excavated pit | Edge protection
87 |  | before commencing traffic deck hacking need to provide localised noise barriers | Environmental
526 | Installed the edge protection to prevent fall | No installation of edge protection at edges. Potential of falling hazard. South plot-V02 PTU | Edge Protection
399 | Ask the Sub contractor to Fully fenced around Generator . | West plot area Generator area not fully fenced . | Electrical
672 | Instructed Sam Lain supervisor to reinste the cover immediately | Entrance B: Apron slab temporary drain cover removed and not reinstated | Floor protection
989 | Instructed area supervisor to clear the stagnent water and maintain the access free from any stagnant water to prevent any slippery hazards | Water ponding along the access at gate 2 | Environmental
835 | Informed to pic electrical hang 2m height & provide insulated S hook.prevent trip& falling hazards. | GL6-7 electrical cable laying on the ground.cable may damage &trip and Falling hazards | Electrical
216 | Good practice, mosquito oil apply on rutine basis | West Plot | Environmental
969 | Tasked a worker nearby to cover sharp edges with unused cloth | Entrance B: Sharp protruding hoarding runner may cause laceration | Protruding Object
696 | LS was informed and get it immediately | Failed to done Lm&LG monthly color code for lorry crane used | Lifting
489 | It was informed GCL pic | Improper barricade provide for the pile excavation pit | Excavation
161 | Immediately get supervisor to clear out stagnant water and canvas. | Gate 1 : unattended canvas collected stagnant water | Environmental
374 | Protected of protruding rebars using by metal troughs. | No rebar protection. South plot-T42, Retaining wall ramp area. | Protruding object
411 | Informed to Zone B PIC provide proper storage . | Poor maintains of storage. | Material storage
419 | It was informed GCL PIC cutaway and make ENV safe | Zone H found Exposed rebar | Protruding object
305 | Get the contractor do it Immediately hard barricade with slope protection. | West plot , Observed Excavation Slope area need to be done hard barricade | Edge protection
471 | Installed “R” pin | Missing of R pin. South plot- U 52. | Supervision
179 |  | Loose materials scattered along the walkway | Access and egress
170 | immediately close back | Floor opening on the Access way | Floor protection
384 | Backfilled the areas | Soil erosion at underneath of scaffold structures. Possibility to structural collapse When losing enough footing strength. South plot-V12 PTU | Excavation
165 |  | Overgrown vegetation along hoarding area, potential mosquitoes breeding ground. | Environmental
386 | Reminded worker to use designated access | Worker are taking short to work location. Could causes of serious injury when hit by G.I pile or fall down from the slopes. South plot-62AD05 | Access and egress
901 | KTH site supervisor notified to fix traffic reflective disc | Zion Road : Work zone may not be conspicuous to road users | Supervision
359 | Instruct supervisor to update | Failed to update monthly LEW sticker. South plot-V12 PTU | Electrical
693 | Briefing to clear immediately... | Cable storage canvas sheet collecting water potential mosquito breeding @ near pant shop . | Environmental
31 |  | Loose materials scattered on working platform,.potential falling object hazard | Falling object
676 | Cautioned them to be on the look out for vehicle from Zion Road entering Holiday Inn slip road | GL1: Hoarding work | Supervision
18 | Instructed supervisor to arrange for the materials stacking | ENT D . Materials storage need to stack properly | Material storage
588 | Woking area poor houskeeping. | 60 Tuas Crescent Plant Yard | Housekeeping
52 | Backfilled the area | Slurry on the walkway. Uneven ground. South plot-V10, PTU | Environmental
883 | I told to safety to clear the stagnant water in entrance B ground level | Entrance B Ground level stagnant water on the ground can cause of mosquito breeding | Environmental
56 |  | Material storage covered canvas collected stagnant water | Environmental
881 | lnform supervisor to housekeeping | Ent G ground level need to housekeeping | Housekeeping
25 |  | PUB send notification to rectify drain grating cover which is generated loud noise while vehicle pass over the grating cover. | Floor protection
731 | Instructed Amxon supervisor to restake the materials with proper maaner | Materials stored inappropriate manner at station box | material storage
66 | It was informed and advised to get rearrange s&p Sup Ramanathan | Zone H poor material storage maintain by S&P | Material storage
1003 | Cape sup was remind to do it immediately | Color code and inspection report failed to done cape eng | Power Tools
222 | Good practice, apply mosquito oil routine basis | West Plot | Environmental
48 | Reminded respective supervisor to present and NO SUPERVISOR NO WORK | No supervisor present while carry out rebar works. South plot-62AD05 | Supervision
924 | Gas cylinder trolley kept on the staircase, people working from the access its may drop and hit people and get injury, have informed people to move in storage | urse Level staircas | Material Storage
956 | Flagged up to project management level via today internal review meeting & email send to involved contractor to address the observation | Professional Engineer appointed by subcon Chuan Lin did not physically inspect the Working Load Test (kentledge) set-up physically on site. The certificate of supervision (COS) whish was issued stated that the inspection took placed on the 27/10/2020 which is the Project rest day (non-working day). | Supervision
220 | Good practice, colume top opening area provide soil to prevent water stagnant | West Plot | Environmental
256 | Unwanted scaffold items clear | West Plot UG/04 | Scaffold
262 | Unwanted scaffold items remove | West Plot UG/08 | Scaffold
414 | It was remind zone Sup and pic | Improper material storage at machinery park area it will chance to Tripp people | Material storage
186 | Single blank put working, inform to them provide double blanks | 63AD05, south | Work at height
765 | Water stagnant area provide soil | South plot T/5 | Environmental
825 | Ask to clear the material near to Access area become Access free obstruction | West plot observed material storage area with access obstruction | Access and Egress
585 | Coordinated with YES Construction WSHC to put up a localise hard barricade at their exposed pipe trench area | Administration building - exposed pipe trench by other contractor (YES construction) within GPL work area. Potential trip & fall hazard. | Access and Egress
252 | No use items remove from work location | West Plot UG-08 | Housekeeping
136 | Inform to PIC and cleared | Zone B scattered material after dismantling pipe under deck | Housekeeping
533 | Ask to Remove unwanted material from that entrants area | West plot , confined space Entrants area with poor housekeeping | Housekeeping
195 | Advised crane operator to keep recording in the logbook regularly. | Failed to update the mobile crane logbook by operator. South plot-62AD05, Basin. | Lifting
968 | Suggest to Amxon to either use steel plate or infill the cavity with sand | Entrance B : Earth pit not effectively covered | Floor protection
102 | Ask to remove the Material from there to dispose | West plot, Observed unwanted material kept it on the ground | Material storage
830 | Rebar protection cap missing and put it back | South plot | Protruding Object
124 | Using scaffolding access for culvert 2 the scaffolding supervisor inspection done Subcon: MAH | South culvert2 | Scaffold
314 | Ask the contractor to remove Immediately | West plot , observed use GI wire to secured the Concrete portable Vibrator . | Hand tools
342 | Instructed supervisor to clean up diverted public area. | Along zion road diverted public walkway observed loose soil and dry leafs. | Housekeeping
306 | Get the contractor to close the opening immediately | West plot , observed Generator Enclosure with opening at R 31 area | Electrical
720 | Notified Sam Lain supervisor to hook up harness at mid rail and lanyard loop over top rail as fall restraint | MH16: Not so effective way to prevent fall | PPE
566 | PIC arranged localised noise barrier close to noise source of machinary to reduce noise level. | East wall surface area , traffic diversion prepration works , premix paving job generates noise. | Environmental
475 | Provided slope protection and warning signages | No provision of slope protection and warning signages at excavation slopes. South plot-T42, Retaining wall ramp areas | Excavation
1004 | It was informed GCL Sup to closed immediately | Construct worker rest area found none protected protruding rebar | Protruding Object
497 | Notified Gammon supervisor to fix acrylic panels expeditiously | Gate 2: incomplete site hoarding with sharp edges | Protruding Object
1000 | Removed and clear | Poor maintains housekeeping the materials collecting water potential mosquito breeding | Housekeeping
919 | Arranged with Aminul to shift the material blocking the access | Upperconcourse GL16-Otis Materials obstructed the access to the Pump Sump Room | Access and Egress
914 | Ask the subcon to shift the materials away from the footpath | Gate 3 Jalan Bukit Ho Swee | Material Storage
598 | Tasked KTH supervisor to reinforced the barricade | Entrances D: Edge protection is flimsy | Edge protection
174 | Observe many rubbish and debris at staircase. Request team to clear and make access safe. | Ent B - Cooling tower staircase | Access and egress
490 | Informed GCL PIC to rectify | Obstruct access path at zone H | Access and egress
57 |  | Unattended / no labelled chemical drum stored with RC drain. | Hazardous substances
41 |  | Good practice: Random check on personnel having their pocket hand sanitizer at south plot. | PPE
229 | Unwanted items clear from chemical mixed drum area | West Plot ECM/02 | Housekeeping
933 | Lew sticker with out use it tools inform to them elec check and provide lew sticker | South, ptu | Electrical
316 | Inform the contractor to tidy up and Clean the area | West plot , scaffold dismantle material untidy / Housekeeping issue | Housekeeping
949 | Immediately remove the canvas sheet and keep at storage. | Poor maintains of canvas sheet lead to water collecting potential mosquito breeding | Environmental
182 |  | Proturding sharp edge object along the accessway, | Protruding object
219 | Good practice, ECM monitoring in rutine basis | West Plot | Environmental
109 |  | housekeeping and damaged canvas collected stagnant water, potential mosquito breeding ground. | Environmental
234 | No use rebar clear and remove tripping hazard | West Plot K/71 | Housekeeping
706 | Informed to pic provide hard barricade or steel plate prevent Trip & falling hazards | Entrance B,apron slab drain opening no have hard barrier.people may Trip & falling hazards. | Floor protection
912 | Informed the subcon to throw all the unnecessary materials at the Entrance. | ENTRANCE A | Housekeeping
574 | Metal hoarding sheets kept on the public footpath due to sharp edges public may get hit and injury. have informed worker to keep storage the metal sheets | Entrance D public footpath | Protruding object
202 | Updated | No update the monthly LEW sticker. South plot-V03, PTU | Electrical
790 | Drain out the drip tray stagnant water | West plot R 31 | Environmental
362 | Cleared the stagnant water and backfilled by sands to prevent mosquitoes larvae breeding. | Found stagnant water underneath of metal waste bin. Potential of mosquitoes larvae breeding. South plot-62AD45 | Environmental
843 | Stop welding works | South culvert 1 | Fire Hazard
727 | Remind, briefing and request safety to follow up for cable hanging. Important, cable must be cleared not inside fatal zone of machine | Ent B - Apron slab GL EB1 - 5 | Electrical
978 | Immediately get area inchagre to carry out housekeeping | Entrance E - material storage on floor area collected stagnant water. | Environmental
483 | Ask the contractor to replaced the barricade | West plot , observed Air compressor Barricade was damaged at P 21 area | Supervision
543 | Timeout for mass housekeeping and clearing of stagnant water ro be conducted. | Gammon storage area potential slip, trip and falls. Health hazard, potential mosquito breedings. | Material storage
682 | Before start generator need to checklist update and check visually in good condition | South culvert 1 | Electrical
474 | Provided red barriers | No provision of fatal zone barricades for roller. South plot-62AD05, Basin | Fatal Zone
974 | Instructed supervisor to replace construction bin. | Covent Garden- construction waste bin overflow | Environmental
347 | Instructed KTG to rearrange mater storage area and provide safe access for maintenance. | Ent D , poor material storage area. | Material storage
162 | Set up maintained well and no breeding recorded. | On site gravitrap- adult mosquitoes surveillance set up inspection carried out | Environmental
520 | Installation of metal beam, worker didn’t wear hand gloves can be get finger injury, have advised to wear hand gloves | Entrance E | PPE
654 | Strictly ask them to close / lock and Comply the with full Electrical requirements | West plot Observed Generator fencing Gate Not Locked | Electrical
943 | Cleared and disposed into general waste bin. | Poor housekeeping. Unwanted materials left at site unattended. South plot-U52 | Housekeeping
70 | Informed to pic provide hardbarricade prevent people falling from height | GL12 surface level missing hard barricade | Floor protection
845 | During Excavation no Fatal zone barriers and no Dewatering Subcontractor: lam hwa | South culvert 2 | Fatal Zone
542 | Yes briefing done to sub contractor | Pilling auger loaded on top of the existing live hydrant (UG) pipe and blocking the islolation valve ( during emergency unable close the valve ) | Underground Utilities
990 | Sharp edges Materials storage with no barricades. Need provide barricade to prevent incidents, it's may caused people injury | Covent garden | Material Storage
862 | Briefing and advice to provide erosion mat and fully cover the expose soil . | Poor maintains of expose soil potential hazard silt water go public drain and can wash sheet water collecting. | Environmental
631 | Pump out water into holding tank to avoid overflow | Water overflowing into public drain due to heavy rain. South plot-ECM 1 | Environmental
876 | Instructed GPL to apply the safe distancing box ( marking with yellow black tape) at the entrance of the office door | Site office - no safe distancing marking in the office container. | Access and Egress
79 | Tasked AMXON banksman to remove few pieces of materials that affect mewp slewing | Entrance B: Stacking of materials may hinder mewp slewing zone | Material storage
944 | Instruct respective supervisor to stack the materials at least 300mm above from the ground. | Poor materials management. G.I pipes are stored direct on the ground at south plot-U52 | Material Storage
986 | As observation - to be more secure and safe. Require lifting team and subcon also to tie concrete block on trailer before remove lifting hook. Concern on topple of concrete block | Gate 12 - CBP hoisting up to trailer | Falling object
541 | Ask them to Remove Since not use / unprotected | West plot Observed Protruding support rebar on the Floor without Protection | Protruding Object
159 | Instructed supervisor to install localised noise barrier at noise source. | Covent Garden, lamp post installation prepration works , hacking activity generates high noise level. | Environmental
296 | Brief workers to close out the barricade to prevent unsafe access | TU5 area | Edge protection
77 | Amxon Supervisor notified to modify the barricade to cater for access | Entrance B: Access blocked by hard barricade | Access and egress
820 | Ask to Tidy up the area and Clear all unwanted material . | West plot , K 71 area Housekeeping and Tidy up the area | Material storage
643 | Brief workers to tidy up the work space | T01 area | Housekeeping
930 | Road damaged, inform to them make it level | South plot main access area | Floor protection
458 |  | Insufficient safe zone barricade provided at work area and workers helmat identification details was not tally as per Covid -19 safe management measures | PPE
341 | Temporary steel mesh use to cover the manhole | S3 Manhole: Raising of manhole to match road level | Floor protection
976 | Immediately intervention and tidy up zone area. | Ent A linkway slope area covered canvas collected stagnant water, potential mosquitoes breeding ground. | Environmental
84 | Instructed supervisor to arrange trimming | Area 1 : along hoarding observed overgrown vegetation | Environmental
580 | Informed GCL PIC to make a safe access for access and egress | Failed to provide safe access to trench work area | Access and egress
213 | No good condition PPE clear from work location | West Plot | PPE
455 | Immediately get supervisor to clear out metal rod to avoid any public injury. | verted public walkway found unattended concrete barrier interlock metal rod. | Access and egress
110 | Ensure fatal zone barricades to machinery | C2 south | Fatal zone
685 | Monthly colour code no update Using to Hoisting objects Subcontractor: ZYG | South culvert 2 | Lifting
867 | Informed sub con Sup to rearrange immediately | Improper material storage at ramp access path | Material storage
308 | Get the contractor to Tidy and Relocate the Material | West plot , Observed material untidy at Formwork dismantle area | Housekeeping
391 | Get the contractor to lock it immediately . | West plot , observed Generator Enclosed door not lock at R 31 area | Electrical
717 | Notified KTH supervisor to avoid stacking the drain in such a manner | GL6 surface : Precast drain not properly stacked and without strapping | Material Storage
326 | Immediately report and briefing gammon PIC and drill gems supervisor to provide proper base plate. | Zone B drill gems No provide proper base plate and cement tank stand. Potential hazard when you load may lead to topple . | Falling object
888 | Inform PIC to cleaning | Entrance B Sam lain BRC not proper for storage | Material storage
339 | Instructed AMXON banksman to focus on mewp slewing | Entrance C: MEWP is positioned between steel column | Work at height
35 | Baricade area no provide signage , inform to them provide signages | Warning sign missing at fence off area | Material storage
655 | Told the contractor to follow up housekeeping and Tidy up material and Relocate with Barricaded | West plot Observed Poor Housekeeping / Material untidy In storage area | Housekeeping
98 | Inform the Contractor to Bring the lock to Lock it | West plot, found Generator mobilised to site Enclosure door Not lock . | Electrical
702 | Every day morning housekeeping work | Site carpark and main access | Housekeeping
931 | Hot weather drink more watet | South, basin 62AD45 | Environmental
454 | Instructed to operator for activate water treatment plant. | Station box roof slab collected ponding water. | Environmental
878 | Instructed Chuan Lin to clear the debris & to locate to one area with barricade instead of leaving it at multiple location obstructing the access way | Technical Building - hacked rc pile debris with protruding rebar was place at common access way area | Access and Egress
982 | Instructed area supervisor to cover cement bags pallet and not in use drum clear out. | Platform area stored cement bags and water drum unattended, potential dust pollution & poor maintenance | Environmental
448 | Identified those potential mosquitoes breeding ground and applied larvaciding. | External pest control service carried out at site | Environmental
633 | Advised to comply buddy system, issued rubber hand gloves and present supervisor for the activity | Working without buddy system,no wearing of proper hand gloves for plastering work and no supervision. South plot-P02 | Supervision
90 | Good practice: hacking works at source provided localised noise barriers. | Covent Garden , drain prepration works provided noise mitigation measures | Environmental
704 | Instructed gpl sup to relocate or to utilise the gi pipe for erection to demarcate gol work area between other contractor | Bromine building - improper housekeeping, scaffold material left in a haphazard manner | Housekeeping
3 | Inform sub PIC to arrange remove Lorry, give free access | Gate 3 water tech parking Lorry at public walkway, not proper access for public walkway | Access and egress
664 | Fire watchman standby for any hot work | C1 south | Fire Hazard
447 | Instructed Amxon supervisor to activate team to tidy up place. | Entrance E - material storage area collected stagnant water, potential mosquitoes breeding ground. | Environmental
353 | Arranged to reinstate the slope | Near Blk 94 bus stop adjacent to public walkway - soil slope to be reinstated to prevent soil erosion. | Environmental
433 | Tasked AMXON to re stack them | Entrance B: Poorly stacked granites | Material storage
86 |  | bared slope area not covered properly, which causes soil erosion ( water pollution) | Environmental
725 | Instructed KTH to stop the work and to fix the the red barricades before resume work | Gate 10 - excavator working without red barrier. | Fatal Zone
137 | Stop them immediately & instructed to use proper platform | Technical building, worker stand on top of formworks | Work at height
772 | Good practice, ECM operation with proper monitoring | West plot | Environmental
680 | Excavator parking no protection for road | South culvert 1 | Floor protection
898 | KTH to assist to backfilled expeditiously | GL4: floor depression along access not backfiiked | Floor protection
838 | Arrange our workers to cleaning | Blk 2B bus stop walkway have ponding water | Environmental
163 | Instructed supervisor to shift chemicals at designated area and clear out stagnant water | Opposite blk 93 , poor material storage | Material storage
43 | Installed edge protection | Missing of edge protection at cable trench opening. Potential of falling hazards. South plot-V12, PTU areas. | Edge protection
345 | Intervened and brief to worker to cover face mask at all time . | East wall - observed worker not covered face mask | PPE
781 | Good practice, before start new task management briefing and related document on site for better understanding. | West plot last IC | Supervision
551 | It was informed in the group to top up hardcore level to prevent stagnant water | Stagnant water at workers rest area | Environmental
330 | Housekeeping work | Site CTQ | Housekeeping
591 | inform to area supervisor to clear the stagnant water and provide drain slope. | Entrance B ground level previous rest area, stagnant water can cause mosquito breeding | Environmental
572 |  | Observed workers using improper working platform with loose planks and without edge protection at Entrance D while carrying out welding works for the glass enclosure steel column | Work at height
856 | Arrange barricades immediately prior proceed any work . | Subcon : Lam Hwa, | Edge Protection
201 | Provided slope protection | No provision of slope protection. Potential of soil when is heavy rain downpour. South plot- T01. | Excavation
1002 | Remind sub con Sup Rubel to replace good ladder and done the ladder checklist before use it | Cape eng failed to done ladder checklist and damaged fall protection of WP used platform ladder | Work At Height
910 |  | Traffic diversion hacking existing premix generated noise pollution and localised noise barrier were placed away from the noise source. | Environmental
629 | Provided toe board | Toe board missing -South plot,T42 (Tank 7) | Scaffold
80 | Tasked KTH supervisor to re align the edge protection | Entrance C: Edge protection not fully enclosing opening | Edge protection
908 | Along zion road diverted public walkway cleaning maintained well. | Green and Caring: Diverted public walkway cleanliness inspection carried out | Housekeeping
273 | Cover the poor maintenance cardothic cables with canvas and plywood | West ppot P 21 | Electrical
945 | Instructed Gammon Supervisor and Banksman to complete interlocked red barricades. | Zone B Gammon, incomplete red barricades for man and machine segregation. | Fatal zone
30 |  | Gaps on the working platform, potential falling object hazard | Scaffold
5 | Immediately inform electrician to rectify | Electrical junction box cover missing at under pass | Electrical
207 | Removed and stored at designated storage area | Unused rebars and metal planks left at site unattended. Potential of tripping hazards. South plot-63AD05, Basin | Material storage
412 | It was informed GCL worker to immediately provide warning barricade to stop lorry when approaching near cable area | Electrical cable cross over the Vehicle Access, it will touch or Entangle by vehicles Ip of body | Electrical
805 | Praise the lifting crew and working team. | Precast ditch installation work: | Lifting
351 | Instructed Amxon supervisor to inspect all water containers and clear out stagnant water. | Station box , observed water drum and containers collected stagnant water. | Environmental
51 | Removed unused items and tidy up the areas | Poor housekeeping: Materials stored direct on the ground. Unnecessary items are dumping in the workplace. South plot-V12, PTU | Housekeeping
421 | Briefing immediately to team and rectified | Zone H found workers walk on the pipe stack and tripping hazard support for the material | Access and egress
97 | Ask contractor clear from there al unwanted material | West plot , Toilet area very Messy unwanted material / poor Housekeeping | Housekeeping
63 | Remind drill gems supervisors and get workers to rectified immediately | Zone B failed to provide barricade for work zone and access where obstructed rest area. | Access and egress
472 | Placed label | No labelling for water bottle. South plot-V12, PTU areas | Hazardous Substances
998 | Cleared and stacked at designated area | Poor housekeeping. Materials are left at site unattended-West plot, R31 | Housekeeping
250 | Silt fence repair | West Plot UG-04 | Environmental
6 | Tasked AMXON lifting Supervisor to shift the hoarding if need to or review the slewing path | Entrance A/ Block 94: Hoarding panel too close to mobile crane counterweight | Lifting
235 | Good practice, work start before do housekeeping the work zone | West Plot K/71 | Housekeeping
502 | Arranged with new vendor adequate portable toilets on site. | Portable toilet was not adequate at workplace. | Environmental
724 | infrom to supervisor and close opening immediately After close | Floor opening no barricades or no proper cover. worker walking time lege can get injury | Floor protection
711 | Informed electrician to install pvc pipe to prevent any damage and electrical shock | Entrance E lighting live wire without protection | Electrical
420 | GCL zone PIC was informed to rectify | Zone H found uneven ground and obstruction big concrete blocks and debris | Access and egress
143 | Arrange excavator clear the debris prevent Trip & falling hazards | GL11.5 to 12.5 roof slab poor house keeping | Housekeeping
749 | Good practice, machine area baricade done | T42, tank 8 | Fatal Zone
768 | Good practice de watering | South plot | Environmental
217 | Good practice, machine follow fetal zone with red barricade | West Plot | Fatal zone
535 | Ask to cover temporary with nail it Display signage . | West plot , Last IC area not cover manhole cover , even though higher level from ground . | Floor Protection
745 | Raining sheet pile area hole , all area fill up done | T42, 62AD47 | Excavation
95 | Get the contractor to Dispose it . | West plot , observed Tank area Poor Housekeeping / unwanted material not Dispose | Housekeeping
746 | Unwanted materials clear | T42, Ramp access | Material Storage
231 | Unwanted items remove | West Plot J/56 | Housekeeping
617 | Vibrator machine no trip tray, inform to them provide | T42 ramp acess | Environmental
517 | Instructed Amxon supervisor to provide adequate protection to prevent any laceration | Protruding sharp edge exposed along the access way at Entrance D | Protruding Object
849 | Good fatal zone management and provision of banksman | Culvert 2 South | Fatal Zone
896 | Tasked KTH worker to expand the fatal to suit the slewing zone | GL 7-10: Fatal zone is narrow for plant to swing without going over the barricade | Fatal zone
874 | Remind Subcon Ss to clear immediately and makes safe environment After | Water stagnant and algae drill gems work area slip and fall hazard | Environmental
902 | Arranged ecm slurry vacuum tanker to carry out water treatment maintenance. | Area 2 : water treatment plant overflow with silt. | Environmental
744 | Disel storage improper place , put inside the chemical storage area | Storage at south | Hazardous substances
623 | Instructed electrician to arrange for LEW inspection | No update the LEW sticker for extension cables -South plot, ECM 1 | Electrical